## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Procure Tablets
Work with GM @ Downtown location to identiy number of tablets needed. |  |  |  | 0 | bar: WEEK 1 M
Work with GM @ North location to identify number of tablets needed. |  |  |  | 0 | bar: WEEK 1 M
Determine if we will purchase and store backup tablets for emergencies |  |  |  | 0 | bar: WEEK 1 M
Assess available tablet options and specs from the supplier that meet requirements. |  |  |  | 0 | bar: WEEK 1 M
Create contract and statements of work for tablet vendor |  |  |  | 2 | bar: WEEK 1 T to WEEK 1 W
Buy and receive the correct number of tablets | Due to disruption in supply line, our originally ordered tablets were unable to arrive in time for launch and should come in a few weeks after launch. |  |  | 10 | bar: WEEK 1 W to WEEK 3 T
Milestone: Prepare for rollout w/ Internal Teams
Connect marketing team with Terrific Tablets for branding and digital menu design |  |  |  | 0 | bar: WEEK 1 W
Work with Carter on possible menu revamp | Is this something that we can hold off on? It potentially blocks the decision for featured menu items and coupon values to display on the tablets |  |  | 10 | Carter | bar: WEEK 1 W to WEEK 3 T
Add featured menu items and coupon values to tablets | Dependent on marketing team designs, as well as identifying featured menu items and coupon values from Peta. Would also be impacted by potential menu revamp from Carter. |  |  | 1 | Deanna, Carter, Marketing | bar: WEEK 3 T
Work with tablet supplier to identify common issues and turn-around times resolving tablet problems. |  |  |  | 2 | Peta | bar: WEEK 1 R to WEEK 1 F
Develop internal policy and troubleshooting guides for the tablet rollout and usage |  |  |  | 3 | Peta | bar: WEEK 1 R to WEEK 2 M
Assess work required to ensure tablets integrate seamlessly with existing POS and host system | In order to work with the tablets, the FlatPlate OS needs to be on version 3.0 |  |  | 3 | bar: WEEK 1 F to WEEK 2 T
Milestone: Tablet Training
Develop a training program and rollout guide |  |  |  | 7 | Peta/Seydou | bar: WEEK 1 R to WEEK 2 F
Pre-training meeting to introduce tablets and changes |  |  |  | 1 | Seydou | bar: WEEK 1 F
Seydou will train GMs and key staff on tablets |  |  |  | 2 | Seydou | bar: WEEK 2 M to WEEK 2 T
Work with GMs to coordinate, schedule, and hold meetings to discuss rollout and report questions/concerns | Be sure to monitor staff response and address any questions |  |  | 7 | bar: WEEK 3 M to WEEK 4 T
Milestone: Tablet Installation
Identify bar section tables that need to be wired properly by electrician |  |  |  | 0 | bar: WEEK 3 T
Install one tablet to ensure proper installation and to identify any potential issues |  |  |  | 0 | bar: WEEK 3 T
Hire electrician to wire appropriate tables at Downtown location | half-days. Let's address any potential issues by intsalling one tablet first and note any issues. |  |  | 3 | bar: WEEK 3 T to WEEK 3 R
Hire electrician to wire appropriate tables at North location | half-days. Let's address any potential issues by intsalling one tablet first and note any issues. |  |  | 3 | bar: WEEK 3 T to WEEK 3 R
Milestone: Test Run
Hold test run with staff family and friends in order to mimic full service |  |  |  | 0 | bar: WEEK 3 F
Collect feedback from test run and identify ways to improve |  |  |  | 1 | bar: WEEK 3 F
Implement feedback from test run |  |  |  | 3 | bar: WEEK 3 F to WEEK 4 T
Milestone: Launch Day
Schedule launch day |  |  |  | 0 | bar: WEEK 1 M
Prepare for launch day by coordinating and identifying outstanding needs from GMs |  |  |  | 2 | bar: WEEK 3 R to WEEK 3 F
Launch day :D |  |  |  | 0 | bar: WEEK 4 T
Milestone: Install Upgraded Devices Post-Launch
Change plugs for new tablets. | Due to disruption in supply line, our originally ordered tablets were unable to arrive in time for launch and should come in a few weeks after launch. |  |  | 2 | bar: WEEK 5 T to WEEK 5 W

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Procure Tablets
Work with GM @ Downtown location to identiy number of tablets needed. |  | 0 | 0 | 0 | 1 | H
Work with GM @ North location to identify number of tablets needed. |  | 0 | 0 | 0 | 1 | H
Determine if we will purchase and store backup tablets for emergencies |  | 0 | 0 | 0 | 1 | H
Assess available tablet options and specs from the supplier that meet requirements. |  | 1 | 1 | 1 | 2 | H
Create contract and statements of work for tablet vendor |  | 2 | 1 | 2 | 3 | H
Buy and receive the correct number of tablets | Due to disruption in supply line, our originally ordered tablets were unable to arrive in time for launch and should come in a few weeks after launch. | 10 | 7 | 10 | 14 | H
Milestone: Installation and setup
Connect marketing team with Terrific Tablets for branding and digital menu design |  | 0 | 0 | 0 | 1 | H
Work with tablet supplier to identify common issues and turn-around times resolving tablet problems. |  | 2 | 1 | 2 | 4 | H
Develop internal policy and troubleshooting guides for the tablet rollout and usage |  | 3 | 1 | 2 | 4 | M
Assess work required to ensure tablets integrate seamlessly with existing POS and host system | In order to work with the tablets, the FlatPlate OS needs to be on version 3.0 | 3 | 1 | 3 | 4 | L
Identify a location to store backup tablets |  | 0 | 0 | 0 | 1 | H
Identify bar section tables that need to be wired properly by electrician |  | 0 | 0 | 0 | 1 | H
Install one tablet to ensure proper installation and to identify any potential issues |  | 0 | 0 | 0 | 1 | M
Hire electrician to wire appropriate tables at Downtown location | half-days. Let's address any potential issues by intsalling one tablet first and note any issues. | 3 | 2 | 3 | 4 | M
Hire electrician to wire appropriate tables at North location | half-days | 3 | 2 | 3 | 4 | M
Add featured menu items and coupon values to tablets | Dependent on marketing team designs, as well as identifying featured menu items and coupon values from Peta. Would also be impacted by potential menu revamp from Carter. | 1 | 0 | 1 | 2 | M
Work with Carter on possible menu revamp | Is this something that we can hold off on? It potentially blocks the decision for featured menu items and coupon values to display on the tablets | 10 | 4 | 10 | 14 | M
Milestone: Tablet Training
Develop a training program and rollout guide |  | 7 | 7 | 7 | 10 | H
Pre-training meeting to introduce tablets and changes |  | 1 | 1 | 1 | 2 | H
Seydou will train GMs and key staff on tablets |  | 2 | 2 | 2 | 3 | H
Work with GMs to coordinate, schedule, and hold meetings to discuss rollout and report questions/concerns | Be sure to monitor staff response and address any questions | 7 | 7 | 10 | 14 | L
Milestone: Test Run
Hold test run with staff family and friends in order to mimic full service |  | 0 | 0 | 0 | 1 | H
Collect feedback from test run and identify ways to improve |  | 1 | 0 | 1 | 2 | M
Implement feedback from test run | Not sure what these tasks might look like... they might range from updating menu to process change | 3 | 1 | 2 | 4 | L
Milestone: Launch Day
Schedule launch day |  | 0 | 0 | 0 | 1 | H
Prepare for launch day by coordinating and identifying outstanding needs from GMs |  | 2 | 1 | 2 | 4 | H
Launch day :D |  | 0 | 0 | 0 | 0 | H
Milestone: Install Upgraded Devices Post-Launch | Due to disruption in supply line, our originally ordered tablets were unable to arrive in time for launch and should come in a few weeks after launch.
Change plugs for new tablets.

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Restaurant Tablets- Is It Worth the Investment? | https://plumpos.com/restaurant-technology/restaurant-tablets.html | 2021-06-15 | Source kitchen monitors to streamline orders to allow the entire kitchen staff to view incoming requests without the struggle of deciphering different servers' handwriting
3 reasons why a tablet ordering system will ruin your restaurant | https://missdetails.com/3-reasons-why-a-tablet-ordering-system-will-ruin-your-restaurant/ | 2021-06-15 | Purchase backup tablets. What happens when a tablet breaks?

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction - faster, more efficient experience | Average ticket time for appetizers ~ 8 minutes and 12-15 minutes for entrees. | Can the back-end staff reasonably accomodate a turn-around time of around eight minutes for appetizers and 12-15 minutes for entrees? | Assess order flow and fulfillment. Track time orders are placed to when they are served. Does the tablet software track this data over time? | FALSE
Customer Satisfaction - faster, more efficient experience | Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback | FALSE
Customer Satisfaction - faster, more efficient experience | Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated/avoided/resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | FALSE
Customer Satisfaction - faster, more efficient experience | 100% order accuracy |  |  | FALSE
Customer Satisfaction - faster, more efficient experience | Average wait time of ten minutes or less before customers are seated | How can we reduce the wait time to under ten minutes? | Track wait times in host system to ensure customers are being seated in under ten minutes. | FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Average ticket time for appetizers ~ 8 minutes and 12-15 minutes for entrees. | Can the back-end staff reasonably accomodate a turn-around time of around eight minutes for appetizers and 12-15 minutes for entrees? | Assess order flow and fulfillment. Track time orders are placed to when they are served. Does the tablet software track this data over time? | How long did it take for you to receive your appetizers? | Multiple choice | 5-10 minutes | 10-15 minutes | more than 15 minutes
Average ticket time for appetizers ~ 8 minutes and 12-15 minutes for entrees. | Can the back-end staff reasonably accomodate a turn-around time of around eight minutes for appetizers and 12-15 minutes for entrees? | Assess order flow and fulfillment. Track time orders are placed to when they are served. Does the tablet software track this data over time? | How long did it take for you to receive your entrees? | Multiple choice | 5-10 minutes | 10-15 minutes | more than 15 minutes
Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback | How long did it take you to complete the checkout process today? | Multiple choice | less than a minute | 1-3 minutes | more than 3 minutes
Checkout time of one minute or less. | What are the benefits to customer experience when they are able to checkout in one minute or less? | Include optional surevy at the end of payment to collect user feedback | How satisfied are you using the tablet to checkout? | Scaled | Very Unsatisfied | Unsatisfied | Neutral | Satisfied | Very Satisfied
Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated/avoided/resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | Did you encounter any issues using the tablet? | Yes/No | Yes. Please explain: | No
Less than 5% of customers who use the tablets report technical issues each week | What are the common technical issues that arise with tablet usage and how can they be mitigated/avoided/resolved? | Research frequent tablet issues and identify ways to approach those issues should they arise. Train staff on those issues and how to resolve. | How was your experience using the tablet to order your meal today? | Open-ended | Please explain:
100% order accuracy | How can we assess customer satisfaction with their meal? | Ask customer via survey if they enjoyed their meal and if they were able to order exactly what they wanted with the tablet | Were you satisfied with your meal today? | Yes/No | Yes | No
100% order accuracy | How can we assess customer satisfaction with their meal? | Ask customer via survey if they enjoyed their meal and if they were able to order exactly what they wanted with the tablet | Were you able to order exactly what you wanted? If no, please explain. | Yes/No | Yes | No. Please explain:
Average wait time of ten minutes or less before customers are seated | How can we reduce the wait time to under ten minutes? | Track wait times in host system to ensure customers are being seated in under ten minutes. | How long did you have to wait before being seated today? | Multiple choice | 0-5 min | 5-10 min | 10-15min | 15 or more min
Average wait time of ten minutes or less before customers are seated | How can we reduce the wait time to under ten minutes? | Track wait times in host system to ensure customers are being seated in under ten minutes. | Were you satisfied with your wait time today? | Scaled | Very Unsatisfied | Unsatisfied | Neutral | Satisfied | Very Satisfied